## Sheet1
key
|  |  | Date | 2022-01-06 | 2022-02-06 | 2022-03-06 | 2022-06-06 | 2022-07-06 | 2022-08-06 | 2022-09-06 | 2022-10-06 | 13/6/2022 | 14/6/2022 | 15/6/2022 | 16/6/2022 | 17/6/2023 | 20/6/2022 | 21/6/2022 | 22/6/2022 | 23/6/2022 | 24/6/2022 | 27/6/2022 | 28/6/2022 | 29/6/2022 | 30/6/2022 | 2022-01-07 | 2022-04-07 | 2022-05-07 | 2022-06-07 | 2022-07-07 | 2022-08-07 | 2022-11-07 | 2022-12-07 | 13/7/2022 | 14/7/2022 | 15/7/2022 | 18/7/2022 | 19/7/2022 | 20/7/22 | 21/7/22 | 22/7/22 | 25/7/22 | 26/7/22 | 27/7/22 | 28/7/22 | 29/7/22 | 31/7/2022 | 2022-01-08 | 2022-02-08 | 2022-03-08 | 2022-04-08 | 2022-07-08 | 2022-08-08 | 2022-09-08 | 2022-10-08 | 2022-11-08 | 14/08/22 | 15/08/22 | 16/08/22 | 17/08/22 | 18/08/22
Task | employee | cost
creating the customer support and management system | junior cloud engineer : cameron middleton | £2304
Creating the customised development, testing and intergration | junior cloud engineer : cameron middleton | £3072
setting up backend for support and development system | cloud engineer : mrugagya mulay | £7920
integration with the companys central system | cloud engineer : mrugagya mulay | £5940
setting up and configuring cloud server | cloud engineer : mrugagya mulay | £7425
installing and configuring local server | senior network engineer : israel shodeinde | £3200
configuring secuirty protocols | senior network engineer : israel shodeinde | £5120
installing network infrastructure | junior network engineer : harry scott | £1656
installing and configuring hardware | senior network engineer : israel shodeinde | £2800
stress testing | software developer : Charlotte Brooks | £6435
software testing | software developer : Charlotte Brooks | £2160
hardware testing | junior network engineer : harry scott | £1656